# Membership Promotion 2005-2008

November 2006, National Széchényi Library, Budapest

2005–2006 has been the most successful recent year for CERL in terms of membership recruitment, following implementation of the Membership Promotion Plan discussed and adopted at the 2005 Annual General Meeting. Six new Full members and two Special members have joined the Consortium.  Negotiations have been concluded with ABINIA for access to the Consortium by special arrangement.

It is clear that this success needs to be maintained in order to allow the Consortium to continue its programmes of development of new technical resources and services for its members. As the coming year is the first of the new three-year funding period, attention has also to be given to the renewal of the existing members’ fees, following the members’ determination of the level of membership fee for the new funding period (see paper FM/2006/3).

The attached table shows the steps (highlighted in green) which have been taken in the 2005–2006 year to implement the Membership Promotion Plan for 2005–2008 which was adopted at last year’s Annual General Meeting.

The Finance Committee in FM/2006/3 has presented a series of developments and changes in the Consortium’s membership structure which, if adopted by the members, will influence the direction of future membership promotion efforts, as it will give some extra flexibility in approaching potential new members and customers.

The table also sets out areas for promotional activity for the period up to 2008, both in the general provision of promotional materials and in campaigns to advertise CERL’s initiatives and services and to attract new members. The development of a new website with additional facilities is intended to be an important part of this activity.

Personal contacts are invaluable in promotion and membership recruitment, and all members are strongly encouraged to continue to assist the Secretariat in publicising CERL to libraries in their countries. Trial periods for the Hand Press Book (HPB) Database are also, of course, available to any interested library on application to the Executive Manager.

action: Members are asked to approve the general outline of the promotional strategy in the following table, and to continue to advise the Secretariat (secretariat@cerl.org) about libraries in their area which might be suitable candidates for membership of CERL and of projects which might be potential customers for access to the HPB.

David Shaw

2 November 2006

| #### Membership category | #### Action | 2005 | 2006 | 2007 | 2008 |
| --- | --- | --- | --- | --- | --- |
| #### General | 1. CERL Website: restructure and redesign | New ‘Provenance Information’ section DONE Specification for new website DONE | Provenance section updated Create new ‘Publications’ section DONE Add PDF files for CERL Papers I–3, HPB leaflets Appoint design team New design IN PROGRESS | Review HPB section in the light of the new contract Develop further features | Review the new design |
|  | #### 2. CERL Literature pack | Revised and expanded DONE | Revise annually; and add information sheets for new initiatives DONE | Revise annually | Revise annually |
|  | 3. CERL Leaflets |  |  |  |  |
|  | #### 3.1 General leaflet | Written, designed and printed (July) Copies sent to IFLA Pre-Conference and IFLA Conference (August) Copies distributed to LIBER libraries in LIBER mailing (August) To be updated and put on website | ##### Revise annually and plan distribution to IFLA and other major events DONE | Revise annually and distribute | Revise annually and distribute |
|  | #### 3.2. Leaflet for Antiquarian booksellers | Designed (July/August) for printing on office printer Sent out to 40 US booksellers | Revise and prepare distribution plans IN PROGRESS | Revise and prepare distribution plans | Revise and prepare distribution plans |
|  | #### 3.3. Publicity leaflet for CERL Papers V | Prepared (August) for printing on office printer Distributed at Provenance conference, Cambridge (September) Insert arranged for the Bibliographical Society’s journal (December) | Find opportunities to distribute Prepare version for CERL Papers VI IN PROGRESS | Find opportunities to distribute Prepare version for CERL Papers VII | Find opportunities to distribute Prepare version for CERL Papers VIII |

|  | #### 3.4 HPB leaflets | Distributed at 3 international conferences and 4 national conferences in 5 number of countries. Put PDF files on new section of website |  |  | Update and reprint as necessary Take forward Spanish and German versions Put PDF files on new section of website DONE |  | Update and reprint as necessary Investigate other language versions | Update and reprint as necessary Investigate other language versions |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | #### 3.5. Other leaflets |  |  |  | Design, produce and distribute: CERL Manuscript Service CERL Thesaurus ##### Mount on website |  |  |  |  |  |
|  | 4. Workshops and seminars |  |  |  |  |  |  |  |  |  |
|  | 4.1. CERL Annual Seminar |  | ‘Many into one’, Biblioteca Nazionale Centrale, Rome, 11 November 2005 Policy document on Annual Seminars prepared. | Organise Seminar at National Széchényi Library, Budapest, 11 November 2006 DONE Select venue and theme for following year DONE |  | Organise Seminar for current year Select venue and theme for following year Review policy document on Annual Seminars |  |  | Organise Seminar for current year Select venue and theme for following year |  |
|  | 4.2. CERL Papers series |  | Edit and publish previous year’s Annual Seminar papers in time for current year’s Seminar. Publicise sales of current and past CERL Papers |  |  |  |  |  |  |  |
|  | 4.3 CERL Workshops |  | Zagreb: March 2005 |  | Estonia; Lyon JUNE 2006 St Petersburg October 2006 | ##### Plans for Madrid meeting have been unsuccessful |  |  | ##### To be arranged |  |
|  | 4.4 Seminars and Conferences: CERL participation |  | ##### IFLA Pre-Conference, Copenhagen Cambridge Tours | ##### Sharp, The Hague ESTC, London |  | To be arranged |  |  | To be arranged |  |
|  | #### 5. Membership enquiries |  | Follow up all membership enquiries (literature; offer of HPB trial password; workshop) |  |  |  |  |  |  |  |
| Full and Group Membership | 6. Country/region promotion * An asterisk indicates countries which have not yet contributed records to the HBP. |  | Latvia * France Italy UK Norway * | Austria * Estonia * Germany Hungary Spain Switzerland * Ireland Luxembourg |  | Australia * Canada * New Zealand * Poland Slovenia USA * Follow up and extend previous contacts |  |  | Japan Follow up and extend previous contacts |  |
|  |  |  |  | Discuss NA membership arrangements with RLG/OCLC |  | Implement post-2006 contract arrangements on membership |  |  |  |  |

|  | 7. Group Membership | New arrangements posted on website and in CERL literature | Promote revised form of Group Membership Discussed with ABES (France) | Seek to create special Group Memberships |  |
| --- | --- | --- | --- | --- | --- |
|  | 8. Special Members |  |  |  |  |
|  | 8.1. Antiquarian booksellers | List of US book trade prepared. Leaflets and letters sent out (September) Contact with ABA (UK) Contacts with ILAB | Follow-up USA IN PROGRESS Prepare list for UK, France, send out letters IN PROGRESS Follow up ILAB Contacts with ABA discussed by Finance Committee | Follow up UK, France Prepare list for Germany, Italy | Prepare list for Belgium, Netherlands Follow up |
|  | 8.2. Auction houses |  | Identify potential targets | Follow up |  |
|  | 8.3. Centres for the Book; Museums |  | Prepare special leaflet Draw up lists and send leaflets | Follow up |  |
|  | 8.4. National non-publicly funded bodies |  | National Trust and National Trust for Scotland (UK) discussed by Finance Committee | Follow up |  |
|  | 8.5. Private historic libraries | Contact made in UK | Follow up; look for new contacts |  |  |
| ## Other arrangements | 9. Special arrangements To be negotiated with Directors | #### ABINIA: negotiations prepared for AGM | ABINIA APPROVED Investigate North Africa | Follow up |  |
|  | 10. Individual access to HPB : For private individuals without institutional access | #### Discuss access mechanisms with RLG | Devise guidelines and implement service: discussed by Finance Committee | Publicise service |  |

# DJS, 24 October 2006